|  | Task | Owner |
| --- | --- | --- |
|  | Set date | Committee |
|  | Book Facility (i.e., James River Country Club) - Coordinate Room/Timeslot arrangement with Dinner set up, order afternoon refreshments | CMember #1 |
|  | Invite Speaker - Arrange Transportation and Lodging - Obtain Fee for Speaker to decide Registration Fee per Participant - Arrange for Speaker’s needs: laptop, LCD projector, screen, flipchart w/markers, sound system | CMember #2 |
|  | Obtain Speaker’s curriculum, outline, handouts and other materials for Presentation | CMember #2 |
|  | Obtain Sponsorship of: - Afternoon Refreshments (approx $150) - Cocktail Hour (two sponsors of $300 each) | CMember #1 |
|  | Register with the various CE authorities (details are in Document Library): - CFP CE: Must register $100 for CE Sponsor Registration, $50 for each Program Registration - CLU CEU: Must register with Prometric online - Attorney MCLE: see below - CPA CPE: No registration required | CMember #3 |
|  | Submit Speaker’s material for Approval to the CE authorities (4-6 weeks in advance of Program): - CFP CE: Must answer questionnaire online at Registration - CLU CEU: Must register online with application for approval - Attorney MCLE: Must register by mail with application for approval - CPA CPE: No Approval necessary | CMember #3 |
|  | Create Invitation (i.e., at Sendomatic.com) - Design Invitation (notify Webmaster of specifics to add to www.peninsulaepc.org Calendar) - Add email addresses from Excel Spreadsheet (initially will the Membership Roster downloaded in Excel format by the Webmaster of www.peninsulaepc.org) - Create Poll questions: Payment choice, Attendance at Dinner, interest in Membership Applications - Create Subject Line and Message for email distribution | CMember #2 |
|  | Create Flyer for posting in Member’s offices: - Post on www.peninsulaepc.org website - Alert Membership to Flyer posted in Document Library at December meeting | CMember #1 |
|  | Submit announcement to local Newspaper for the Community Events Editor 4-6 weeks in advance of event (appears on Thursdays in the Daily Press) | CMember #1 |
|  | Send Email Invitation blast via Sendomatic.com | CMember #2 |
|  | Have Webmaster of www.peninsulaepc.org send FAX Invitations to members without email | CMember #2 |
|  | Track Invitation RSVP’s - Periodically review Sendomatic.com for updates - Take phone calls from FAXed members and review email correspondence from Members | CMember #2 |
|  | Send Follow Up email blasts from Sendomatic.com to those who have not RSVP’d | CMember #2 |
|  | Create Attendance List Checklist from Sendomatic.com into Excel Spreadsheet for the Registration Desk | CMember #2 |
|  | Create Sign In sheets for each CE Discipline: CFP, CLU, CPA and Attorney - Printed Name, Signature, Time In, Time Out, Signature - CFP License # or State Insurance License # or SS# or VBA# | Secretary |
|  | Create Sponsor Thank You signs for Refreshments and Cocktail Hour | Secretary |
|  | Set up and manage Registration Desk: direct Participants to Sign In sheets and collect Payment | Secretary |
|  | Create Participant Survey for use at the end of the Seminar (template available in Document Library) | CMember #1 |
|  | Create Certificates of Completion for each participant (template available in Document Library) | CMember #1 |
|  | Provide Payment to Speaker at the event | Treasurer |
|  | Send Thank you letters to Sponsors with Invoices (if not paid) | Secretary |
|  | Send Thank you letter to Speaker (template available in Document Library) | Secretary |
|  | Submit necessary follow up data to CE authorities: - CFP CE: Electronic submission of Participant Roster using their Excel Spreadsheet format (on the CFP Board website) - CLU CEU: Electronic submission of Participant Roster to Prometric - Attorney MCLE: No follow up needed after Approval was granted - CPA CPE: No follow up needed | CMember #3 |
|  | Cross check Participant Sign In sheets with Checks paid (from PO Box or Paid-at-the-Door) | Treas/Secret |
|  | Deposit all Checks Received | Treasurer |
|  | COMMITTEE MEMBER #1 -- TASKS |  |
|  | Book Facility (i.e., James River Country Club) - Coordinate Room/Timeslot arrangement with Dinner set up, order afternoon refreshments | CMember #1 |
|  | Obtain Sponsorship of: - Afternoon Refreshments (approx $150) - Cocktail Hour (two sponsors of $300 each) | CMember #1 |
|  | Create Flyer for posting in Member’s offices: - Post on www.peninsulaepc.org website - Alert Membership to Flyer posted in Document Library at December meeting | CMember #1 |
|  | Submit announcement to local Newspaper for the Community Events Editor 4-6 weeks in advance of event (appears on Thursdays in the Daily Press) | CMember #1 |
|  | Create Participant Survey for use at the end of the Seminar (template available in Document Library) | CMember #1 |
|  | Create Certificates of Completion for each participant (template available in Document Library) | CMember #1 |

|  | COMMITTEE MEMBER #2 -- TASKS |  |
| --- | --- | --- |
|  | Invite Speaker - Arrange Transportation and Lodging - Obtain Fee for Speaker to decide Registration Fee per Participant - Arrange for Speaker’s needs: laptop, LCD projector, screen, flipchart w/markers, sound system | CMember #2 |
|  | Obtain Speaker’s curriculum, outline, handouts and other materials for Presentation (provide to CM#3) | CMember #2 |
|  | Create Invitation (i.e., at Sendomatic.com) - Design Invitation (notify Webmaster of specifics to add to www.peninsulaepc.org Calendar) - Add email addresses from Excel Spreadsheet (initially will the Membership Roster downloaded in Excel format by the Webmaster of www.peninsulaepc.org) - Create Poll questions: Payment choice, Attendance at Dinner, interest in Membership Applications - Create Subject Line and Message for email distribution | CMember #2 |
|  | Send Email Invitation blast via Sendomatic.com | CMember #2 |
|  | Have Webmaster of www.peninsulaepc.org send FAX Invitations to members without email | CMember #2 |
|  | Track Invitation RSVP’s - Periodically review Sendomatic.com for updates - Take phone calls from FAXed members and review email correspondence from Members | CMember #2 |
|  | Send Follow Up email blasts from Sendomatic.com to those who have not RSVP’d | CMember #2 |
|  | Create Attendance List Checklist from Sendomatic.com into Excel Spreadsheet for the Registration Desk | CMember #2 |

|  | COMMITTEE MEMBER #3 – TASKS |  |
| --- | --- | --- |
|  | Register with the various CE authorities (details are in Document Library): - CFP CE: Must register $100 for CE Sponsor Registration, $50 for each Program Registration - CLU CEU: Must register with Prometric online - Attorney MCLE: see below - CPA CPE: No registration required | CMember #3 |
|  | Submit Speaker’s material for Approval to the CE authorities (4-6 weeks in advance of Program): - CFP CE: Must answer questionnaire online at Registration - CLU CEU: Must register online with application for approval - Attorney MCLE: Must register by mail with application for approval - CPA CPE: No Approval necessary | CMember #3 |
|  | Submit necessary follow up data to CE authorities: - CFP CE: Electronic submission of Participant Roster using their Excel Spreadsheet format (on the CFP Board website) - CLU CEU: Electronic submission of Participant Roster to Prometric - Attorney MCLE: No follow up needed after Approval was granted - CPA CPE: No follow up needed | CMember #3 |

|  | TREASURER/SECRETARY -- TASKS | OWNER |
| --- | --- | --- |
|  | Create Sign In sheets for each CE Discipline: CFP, CLU, CPA and Attorney - Printed Name, Signature, Time In, Time Out, , Signature - CFP License # or State Insurance License # or SS# or VBA# | Secretary |
|  | Create Sponsor Thank You signs for Refreshments and Cocktail Hour | Secretary |
|  | Set up and manage Registration Desk: direct Participants to Sign In sheets and collect Payment | Secretary |
|  | Provide Payment to Speaker at the event | Treasurer |
|  | Send Thank you letters to Sponsors with Invoices (if not paid) | Secretary |
|  | Send Thank you letter to Speaker (template available in Document Library) | Secretary |
|  | Cross check Participant Sign In sheets with Checks paid (from PO Box or Paid-at-the-Door) | Treasurer/ Secretary |
|  | Deposit all Checks Received | Treasurer |